## PERT
estimations
Activities | predecessors | pesimistic | most likely | optimistic | expected | variance | Exp. ES | Exp. EF | Exp. LS | Exp. LF | Critical path
Start |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
A |  | 2 | 3 | 4 | 3 | 0.11111 | 0 | 3 | 0 | 3 | YES
B | A | 3 | 5 | 7 | 5 | 0.44444 | 3 | 8 | 3 | 8 | YES
C | B | 7 | 10 | 11 | 9.6667 | 0.44444 | 8 | 17.6667 | 8 | 17.6667 | YES
D | C,E | 4 | 5 | 9 | 5.5 | 0.69444 | 17.6667 | 23.1667 | 17.6667 | 23.1667 | YES
E |  | 5 | 7 | 9 | 7 | 0.44444 | 0 | 7 | 10.6667 | 17.6667 | NO
F | D | 4 | 4 | 4 | 4 | 0 | 23.1667 | 27.1667 | 23.1667 | 27.1667 | YES
G | E | 1 | 4 | 6 | 3.8333 | 0.69444 | 7 | 10.8333 | 23.3333 | 27.1667 | NO
Finish | [6 empty] | 27.1667
[8 empty] | Standard deviation of the project duration |  |  |  | 1.3017
PERT Result
We suppose that the duration of the project follows normal distribution with mean
| 27.1667 | and standard deviation |  | 1.3017 | .
| Questions | [7 empty] | Answers
| What is the probability that we finish the project in 26 weeks? | [7 empty] | 0.18506
| What is the probability that the duration of the project will be more than 28 weeks? | [7 empty] | 0.26103
| What is the duration of the project that will not be exceeded with a probability of 0.9? | [7 empty] | 28.8349
Note on H11: Jana Klicnarová: Expected duration of the project.