## Slide 1: Systems Analysis and Design

## Slide 2: Learning Objectives
Explain the process of managing an information systems project.
Describe the skills required to be an effective project manager.
List and describe the skills and activities of a project manager during project initiation, project execution, and project closedown.
Explain what is meant by critical path scheduling and describe the process of creating Gantt charts and Network diagrams.
Explain how commercial project management software packages can be used to assist in representing and managing project schedules.

## Slide 3: Figure 3-1 Three computer applications at Pine Valley Furniture: Order Filling, Invoicing, and Payroll

## Slide 4: Pine Valley Furniture (PVF)
Manufactures high-quality wood furniture
Distributes to retail stores within the U.S.
Started in the early 1980s and expanded by 1984 doubling sale volume
By 1990, Pine Valley Furniture had become a complex company, employing over 50 persons
Company organized into functional areas:
  Sales
  Manufacturing
  Orders
  Accounting
  Purchasing
Established manual information systems

## Slide 5: PVF
PVF installed a network server to automate invoicing, accounts receivable, and inventory control applications.
In the late 1990s, PVF upgraded the network server and implemented a centralized database management system.
PVF decided to develop its application software in-house.
PVF hired staff and bought computer software and hardware.
The new information system will take into account market conditions, the Internet, and WWW.
The Project Manager plays the key role in developing the new information system

## Slide 6: Managing the Information Systems Project
Focus of project management
  To ensure that information system projects meet customer expectations
    Delivered in a timely manner
    Meet time constraints and requirements

## Slide 7: Managing the Information Systems Project
Project Manager
  Systems Analyst responsible for:
    Project initiation (SSR is created)
      user observed the problem
      User contact the IS group
      SSR was reviewed
      Steering committee was assigned
      Detailed project plan was developed.
    Planning
    Execution
    Closing down

## Slide 8: Managing the Information Systems Project
Project Manager is a system analyst with a diverse set of skills such as:
    Management
    Leadership
    Technical
    Problem solving
    Conflict management
    Customer relations
    Team management
    Risk and change management
whose responsible for initiating, planning, executing and closing down a project.

## Slide 9: Managing the Information Systems Project
Project is a planned undertaking of related activities to reach an objective that has a beginning and end.
Deliverable is an end product of an SDLC phase.
Feasibility Study, is a study that determine if the proposed system make sense for the organization from an economic and operational standpoint.

## Slide 10: Project Management Process
Project Management is a controlled process of initiating, planning, executing, and closing down a project.
Project
  Planned undertaking of related activities to reach an objective that has a beginning and an end
Four Phases of PM
  Initiation
  Planning
  Execution
  Closing down

## Slide 11: Project Management Activities

## Slide 12: Initiating the Project
Project initiation – the first phase of the project management process in which activities are performed to assess the size, scope, and complexity of the project and to establish procedures to support later project activities
Establish project initiation team
Establish relationship with customer
Establish project initiation plan
Establish management procedures
Establish project management environment and workbook
Project workbook – an online or hard-copy repository for all project correspondence, inputs, outputs, deliverables, procedures, and standards that are used

## Slide 13: Project Workbook

## Slide 14: Project charter
  A project charter
    Project charter – a short, high-level document prepared for both internal and external stakeholders
    It formally announces the establishment of the project.
    It briefly describes its objectives, key assumptions, and stakeholders.

## Slide 15: Planning the Project
Project planning is the second phase of the PM process, which focus on defining clear, discrete activities and the work needed to complete each activity within a single project.

## Slide 16: Activities of Planning the Project
Describe project scope, alternatives and feasibility
  Scope and Feasibility
    Understand the project
    What problem is addressed
    What results are to be achieved
    Measures of success
    Completion criteria

## Slide 17: Activities of Planning the Project continues
Divide the project into manageable tasks
  Work Breakdown Structure (WBS) – the process of dividing the project into manageable tasks and logically ordering them
  Gantt chart – a graphical representation of a project that shows each task as a horizontal bar whose length is proportional to its time for completion
Estimate resources and create a resource plan
  Constructive Cost Model (COCOMO) – a widely used method which uses parameters that are derived from prior projects of differing complexity
  COCOMO uses these different parameters to predict human resource requirements for basic, intermediate, and very complex systems.
Develop a preliminary schedule
    Utilize Gantt and PERT charts

## Slide 18: Activities of Planning the Project continues
Develop a communication plan
  Outline communication processes among customers, team members and management
    Who are the stakeholders for this project?
    What information does each stakeholder need?
    When, and at what interval, does this information need to be produced?
    What sources will be used to gather and generate this information?
    Who will collect, store, and verify the accuracy of this information?
Determine project standards and procedures
  Specify how deliverables are tested and produced
  During this activity, you will specify how various deliverables are produced and tested by you and your project team.

## Slide 19: Activities of Planning the Project continues
Identify and assess risk
  Identify sources of risk
  Estimate consequences of risk
Create a preliminary budget
  preliminary budget outlines the planned expenses and revenues associated with your project.
Develop a statement of work
  Developed primarily for the customer
  Outlines work that will be done and clearly describes what the project will deliver
  Provides a clear understanding of project size, duration, and outcomes
Set a Baseline Project Plan
  Provides an estimate of the project’s tasks and resource requirements and is used to guide the next project phase – execution

## Slide 20: Planning the project
Gantt chart: a graphical representation of a project that shows task as a horizontal bar whose length is proportional to its time for completion.
Pert chart: a diagram which shows project tasks and their interrelationships. (Program Evaluation Review Technique)
Example of both charts after few slides.

## Slide 21: Activities of Executing the Project
Execute Baseline Project Plan
  Acquire and assign resources
  Train new team members
  Keep project on schedule
Monitor project progress
  Adjust resources, budget and/or activities

## Slide 22: Activities of Executing the Project continues
Manage changes to Baseline Project Plan
  Slipped completion dates
  Changes in personnel
  New activities
  Bungled(clumsily, inadequately) activities
Maintain project workbook
Communicate project status
  Meetings, status reports, meeting minutes, seminars and workshops, bulletin boards, memos, specification documents, brown bag lunches, hallway discussions, newsletters, and project workbook

## Slide 23: Activities of Closing Down the Project
Termination, the final phase of the project management process that focuses on bringing a project to an end
  Types of termination
    Natural
      Requirements have been met
    Unnatural
      Project stopped
  Documentation
  Personnel Appraisal

## Slide 24: Activities of Closing Down the Project continues
Conduct post-project reviews
  Determine strengths and weaknesses of:
    Project deliverables
    Project management process
    Development process
Close customer contract- CSR or SSR.

## Slide 25: Representing and Scheduling Project Plans
Gantt Charts
  Useful for depicting simple projects or parts of large projects
  Show start and completion dates for individual tasks
PERT Charts
  Program Evaluation Review Technique) – a technique that uses optimistic, pessimistic, and realistic time estimates to calculate the expected time for a particular task.

## Slide 26: Calculating Expected Time Durations using PERT
Formula for Estimated Time:
  ET = (o + 4r + p)/6
Where
  ET = expected time for the completion of an activity.
  o = optimistic completion time for an activity.
  r = realistic completion time for an activity.
  p = pessimistic completion time for an activity.

## Slide 27: Figure 3-16 Graphical diagrams that depict project plans (a) A Gantt Chart (b) A PERT chart

## Slide 28: Comparison of Gantt and PERT Charts
Gantt
  Visually shows duration of tasks
  Visually shows time overlap between tasks
  Visually shows slack time
PERT
  Visually shows dependencies between tasks
  Visually shows which tasks can be done in parallel
  Shows slack time by data in rectangles

## Slide 29: Gantt and PERT Charts for Pine Valley Furniture
Steps to construct the chart:
  Identify each activity
    Requirements Collection
    Screen Design
    Report Design
    Database Design
    User Documentation
    Software Programming
    Installation and Testing

## Slide 30: Gantt and PERT Charts for Pine Valley Furniture
  Determine time estimates and expected completion times for each activity, Estimated Time= (O+4R+P)/6 where O is optimistic time, R realistic time, and P is pessimistic time.
  Determine sequence of activities
  Determine critical path
    Sequence of events that will affect the final project delivery date

## Slide 31
Slack time – the amount of time that an activity can be delayed without delaying the project.
Free slack refers to the amount of time a task can be delayed without delaying the early start of any immediately following tasks.
Total slack refers to the amount of time a task can be delayed without delaying the completion of the project.

## Slide 32: Why Using Project Management Software
Many systems are available to help you manage a development project.
Three activities required to use when managing a project:
  Establish project start or end date
  Enter tasks and assign task relationships
  Select scheduling method to review project reports, such as Gantt or PERT chart.