## Slide 1: Systems Analysis and Design

## Slide 2: Learning Objectives
Describe steps involved in the project initiation and planning process (the first two phases of project management)
Explain the need for and the contents of a Statement of Work and Baseline Project Plan
List and describe various methods for accessing project feasibility

## Slide 3: Learning Objectives
Describe the differences between intangible and tangible costs and benefits and between recurring and one-time benefits and costs
Detail various methods of cost/benefit analysis
Describe the general rules for evaluating the technical risks associated with a systems development project
Describe the activities and participant roles within a structured walkthrough

## Slide 4: Initiating and Planning Systems Development Projects
What must be considered when making the decision on the division between project initiation and planning (PIP) and analysis.
How much effort should be expended on the PIP process?
Who is responsible for performing the PIP process?
Why is PIP such a challenging activity?

## Slide 5: The Process of Initiating and Planning IS Development Projects

## Slide 6: The Process of Initiating and Planning IS Development Projects
Project initiation focuses on activities designed to assist in organizing a team to conduct project planning.
Establishing the Project Initiation Team.
Establishing a Relationship with the Customer

## Slide 7: Initiating and Planning System Development Projects
Elements of Project Initiation
  Establishment of project team
  Development of relationship with customer
  Establishing the project Initiation Plan
  Establishment of Management Procedures
  Establishment of Project Workbook and Project Management Environment

## Slide 8: The Process of Initiating and Planning IS Development Projects
The key activity of project initiation is the development of the project charter.
  A short document that is prepared for both internal and external stakeholders.
  Provides a high-level overview of the project.
  Useful communication tool that helps to assure that the organizations and other stakeholders understand the initiation of a project

## Slide 9: The Process of Initiating and Planning IS Development Projects
A project charter typically contains:
  Project title and date of authorization
  Project manager name and contact information
  Customer name and contact information
  Projected start and completion dates

## Slide 10: The Process of Initiating and Planning IS Development Projects
  Key stakeholders, project role, and responsibilities
  Project objectives and description
  Key assumptions or approach
  Signature section for key stakeholders

## Slide 11: The Process of Initiating and Planning IS Development Projects
The key activity of project planning is the process of defining clear, discrete activities and the work needed to complete each activity within a single project.
The objective of the project planning process is the development of a Baseline Project Plan (BPP) and the Project Scope Statement (PSS)

## Slide 12: Project Planning
Is the process of defining clear, discrete activities and the work needed to complete each activity, the elements are:
- describe the project scope, alternative, and feasibility. - Divide project into manageable tasks. - Estimate resources, and create resource plan. - Developing a preliminary schedule. - Developing a communication plan. - Determining project standards and procedures. - Identifying and assessing risks. - Creating a preliminary budget. - Developing a Statement Of Work. - Setting a Baseline Project Plan.

## Slide 13: Initiating and Planning System Development Projects
Major Deliverables and Outcomes of the plan:
  Business Case
    Justification for an information system.
    Presented in terms of the tangible and intangible economic benefits and costs.
    The technical and organizational feasibility of the proposed system
  Project Scope Statement (PSS)
    A document prepared for the customer.
    Describes what the project will deliver.
    Outlines at a high level all work required to complete the project. \
  Baseline Project Plan (BPP), contains the best estimates of :
    A major outcome and deliverable from the PIP phase.
    Contains the best estimate of a project’s scope, benefits, costs, risks, and resource requirements.
  Statement of Work (SOW)
    Describes deliverables
    Outlines work needed to be performed

## Slide 14: Assessing Project Feasibility
Six Categories of feasibility:
  Economic
  Technical
  Operational
  Schedule
  Legal and contractual
  Political

## Slide 15: Assessing Economic Feasibility
A process of identifying the financial benefits and costs associated with a development project.
  Often referred to as cost-benefit analysis.
  Project is reviewed after each SDLC phase in order to decide whether to continue, redirect, or kill a project.
  Determine Benefits
  Tangible Benefits
    Refer to items that Can be measured easily
      Examples
        Cost reduction and avoidance
        Error reduction
        Increased flexibility
        Increased speed of activity
        Improved management planning and control
        Opening new markets and increasing sales opportunities

## Slide 16: Assessing Economic Feasibility
  Intangible Benefits
    are benefits derived from the creation of an information system that cannot be easily measured in dollars or with certainty. Cannot be measured easily
    Examples
      Increased employee morale
      Competitive necessity
      More timely information
      Promotion of organizational learning and understanding
Determine Costs
  Tangible Costs
    a cost associated with an information system that can be measured in dollars and with certainty.
    IS development tangible costs include:
      Hardware costs,
      Labor costs, or
      Operational costs including employee training and building renovations.

## Slide 17: Assessing Economic Feasibility
Determine Costs (Continued)
  Intangible Costs
    a cost associated with an information system that cannot be easily measured in terms of dollars or with certainty.
      Intangible costs can include:
        Loss of customer goodwill,
        Employee morale, or
        Operational inefficiency.

## Slide 18: Assessing Economic Feasibility
  One-Time Costs
    Associated with project startup, initiation and development
    Includes
      System Development
      New hardware and software purchases
      User training
      Site preparation
      Data or system conversion

## Slide 19: Assessing Economic Feasibility
  Recurring Costs
    a cost resulting from the ongoing evolution and use of a system.
      Examples of these costs include:
        Application software maintenance,
        Incremental data storage expenses,
        Incremental communications,
        New software and hardware leases, and
        Supplies and other expenses (i.e. paper, forms, data center personnel).

## Slide 20: Determining Project Costs
Both one-time and recurring costs can consist of items that are fixed or variable in nature.
Fixed costs are billed or incurred at a regular interval and usually at a fixed rate.
Variable costs are items that vary in relation to usage

## Slide 21: Determining Project Costs
Procurement
  Consulting, equipment, site preparation, capital, management time
Start-up
  Operating systems, communications installation, personnel hiring, organizational disruption
Project-related
  Application software, software modification, personnel overhead, training, data analysis, documentation
Operating
  System maintenance, rental, asset depreciation, operation and planning

## Slide 22: The Time Value of Money
Net Present Value (NPV)
  Use discount rate to determine present value of cash outlays and receipts
Return on Investment (ROI)
  Ratio of cash receipts to cash outlays
Break-Even Analysis (BEA)
  Amount of time required for cumulative cash flow to equal initial and ongoing investment

## Slide 23: The Time Value of Money
Time value of money (TVM): the concept that money available today is worth more than the same amount tomorrow.
Discount rate: the rate of return used to compute the present value of future cash flows (the cost of capital).
Present value: the current value of a future cash flow

## Slide 24: The Time Value of Money
Net Present Value
  PVn = present value of Y dollars n years from now based on a discount rate of i.
  NPV = sum of PVs across years.
  Calculates time value of money.

## Slide 25: Assessing Technical Feasibility
Technical Feasibility, a process of assessing the development organization’s ability to construct a proposed system.
The potential consequences of not assessing and managing risks can include the following:
  Failure to attain expected benefits from the project,
  Inaccurate project cost estimates,
  Inaccurate project duration estimates,
  Failure to achieve adequate system performance levels, and
  Failure to adequately integrate the new system with existing hardware, software, or organizational procedures.

## Slide 26: Project Risk Factors
Project size
  Team size, organizational departments, project duration, programming effort
Project structure
  New vs. renovated system, resulting organizational changes, management commitment, user perceptions
Development group
  Familiarity with platform, software, development method, application area, development of similar systems
User group
  Familiarity with IS development process, application area, use of similar systems

## Slide 27: Assessing Technical Feasibility
Risk can be managed on a project by:
  Changing the project plan to avoid risky factors,
  Assigning project team members to carefully manage the risky aspects,
  Setting up monitoring methods to determine whether or not potential risk is, in fact, materializing.

## Slide 28: Assessing Technical Feasibility
Four general rules emerged as technical risk assessments:
  Larger projects are riskier than smaller projects.
  A system in which the requirements are easily obtained and highly structured will be less risky than one in which requirements are messy, ill structured, ill defined, or subject to the judgment of an individual.
The development of a system employing commonly used or standard technology will be less risky than one employing novel or nonstandard technology.
A project is less risky when the user group is familiar with the familiar with the systems development process and application area than if unfamiliar.

## Slide 29: Assessing Technical Feasibility

## Slide 30: Assessing Other Project Feasibility Concerns
Operational
  Does the proposed system solve problems or take advantage of opportunities?
Scheduling
  Can the project time frame and completion dates meet organizational deadlines?
Legal and Contractual
  What are legal and contractual ramifications of the proposed system development project?
Political
  How do key stakeholders view the proposed system?

## Slide 31: Building the Baseline Project Plan
Baseline Project Plan (BPP) is a document intended primarily to guide the development team.
Sections:
  Introduction
  System description
  Feasibility assessment
  Management issues

## Slide 32: Building the Baseline Project Plan
Project Scope statement is part of the BPP introduction.
Sections:
  Problem statement
  Project objectives
  Project description
  Business benefits
  Deliverables
  Expected duration

## Slide 33: Factors in Determining Scope
Organizational units affected by new system
Current systems that will interact with or change because of new system
People who are affected by new system
Range of potential system capabilities

## Slide 34: Diagram Depiction of Project Scope

## Slide 35: Building the Baseline Project Plan (CONT..)
System description section outlines possible alternative solutions.
Feasibility assessment section outlines issues related to project costs and benefits, technical difficulties, and other such concerns.
Management issues section outlines a number of managerial concerns related to the project

## Slide 36: Reviewing the Baseline Project Plan
Structured Walkthroughs: a peer-group review of any product created during the system development process
Roles: coordinator, presenter, user, secretary, standard-bearer, maintenance oracle
Can be applied to BPP, system specifications, logical and physical designs, program code, test procedures, manuals and documentation
Objectives
  Assure conformity to organizational standards
  All parties agree to continue with project